## Implementation Schedule
Fierce Rollout Timeline (Sample Timeline - timelines vary for every organization)
Phase | Audience | What | When | Who | How | Frequency | The Message | Templates and Resources
I: Introduction to the Fierce Conversation Training Series | Internal Sponsor/ Implementation Team | Implementation Strategy Meetings | Week 1-2 | Fierce Implementation Partner | Meeting | Weekly | Agenda: - Provide overview of implementation strategy - Walk through Fierce Rollout Playbook - Uncover obstacles, learn about company culture and readiness for Fierce Trainings - Talk through workshop scheduling for client participants | Guide to Creating a Fierce Conversations Communication Plan for your Organization Fierce Approach and Partnership Overview
| All Audiences | Fierce Introductory Trailer | Week 2-3 | Internal Sponsor | Email | As Needed | Include a link to to this video in the introductory communications | Fierce: Any Conversation Can Video
| Executive Leadership | Communication to Introduce to Fierce Conversations to Organization | Week 2 | Internal Sponsor | Email | Once | Overview of Fierce Conversation and Modules - include dates for intro presentation | Introductory Email Template for Executive Leadership
| Mid Level Managers | Communication to introduce to Fierce Conversations to Organization | Week 2 | Internal Sponsor | Email | Once | Overview of Fierce Conversation and Modules - include dates for intro presentation | Introductory Email Template for Mid Level Managers
| Employees | Communication to introduce to Fierce Conversations to Organization | Week 3 | Internal Sponsor | Email | Once | Overview of Fierce Conversation and Modules - include dates for intro presentation | Introductory Email Template for Employees
| Executive Leadership | Introductory Presentation | Week 3 | Internal Sponsor | Presentation |  | Provide a 30-45 minute overview of the Fierce series to help influencers understand the program and their part in making the training programming successful. | Introductory Powerpoint for Leadership
| People Leaders | Introductory Presentation | Week 3 | Internal Sponsor | Presentation |  | Provide a 30-45 minute overview of the Fierce series to help influencers understand the program and their part in making the training programming successful. This is a great opportunity to gather input on the best way to rollout the training in terms of cohorts, Fierce Conversation module selections, scheduling, etc. | Introductory Powerpoint for Leadership
| Employees | Introductory Presentation | Week 3 | Internal Sponsor | Presentation |  | Provide a 30-45 minute overview of the Fierce series to help employees understand the program, expectations, and answer any questions they may have. | Introductory Powerpoint for Employees
| Participants | Schedule the Workshop(s) | Week 6 | Internal Sponsor | Outlook | For Each Module | Begin scheduling workshops and sending invitations to the selected participants. | Pre-workshop Email Template
| All Employees | Pre-Fierce Benchmarking Survey | Week 6 | Internal Sponsor | Email | Twice (Pre/Post Training) | Gather insights on the current communication culture in the following areas: - Input & Decision-Making - Development & Problem Solving - Role Clarity and Time Management - Feedback Culture - Ownership & Results - Conflict & Authority - Influence, Persuasion, & Consulting | Fierce Benchmarking Survey
| Managers and Leaders | Training for Managers and Leaders | Week 7-10 | Internal Sponsor | Email |  | Introduction to the Fierce Platform & App - include workbook and article links - include link to Fierce Connect app - include link and instructions to digital platform | Introductory Letter to Employees Registered for Fierce Introductory Video to Digital Platform
| All Employees | Announce Fierce On Demand to Learners |  |  |  |  | If utilizing the Fierce Digital Platform: Introduce the Fierce Digital Platform to users prior to giving them access to their accounts. - include Digital Platform Overview - include features and how to access - connect with Fierce IT team to give learners access | Fierce Digital Platform Overview
Phase | Audience | What | When | Who | How | Frequency | The Message | Templates and Resources
II: Training Workshops Begin | First Cohort of Participants | Pre-workshop Communication | One Week Prior to Workshop | Internal Sponsor | Email | Once | Introduction the Workshop - what to expect - how to prpare - include thought provoking questions that are module specific - logistics (date/time/zoom link/location) | Pre-workshop Email Template
| First Cohort of Participants | Day of Workshop Reminder | Day of Workshop | Internal Sponsor | Email | Once | Reminder - include workbook or link to digital platform where learners download the workbooks - include prompts to come prepared to be here and nowhere else - include location and time/zoom link for virtual workshops | Workshop Reminder Email Templates
| First Cohort of Participants | Fierce Conversations Workshop | Day of Workshop | Fierce Certified Facilitator (Internal or Fierce Master Facilitators) | Virtual/Live Meeting | Depends on internal schedule | Deliver Fierce Workshops! | Facilitator Guide, Slide Deck and Participant Workbooks provided for certified facilitators in the Fierce Digital Platform.
| First Cohort of Participants | Post Workshop Communication | Day After Workshop | Internal Sponsor | Email | Once | Provide list of resources for retention - include post workshop articles - include dates of Fierce Fireside Chats - include ideas for application - include summary of Fierce concepts | Post Workshop Email Templates
Phase | Audience | What | When | Who | How | Frequency | The Message | Templates and Resources
III: Learning Transfer and Sustainability | All Fierce For Life Members | Fierce Connect App | Within a week of completing Foundations | Internal Sponsor | Email | As Needed | Introduce the Fierce Connect App to learners right after they've completed their Foundations training. - include Fierce Connect Overview - share highlights of the app and how to gain access - connect with Fierce IT team to ensure learners get access - drive culture change by initiating weekly conversation starters through the My Coach feature | Fierce Connect Overview
| All Fierce participants | Fierce Digital Platform | Within first week of workshop | Internal Sponsor | Email | Quarterly | Remind learners of their access to additional learning tools and refreshers in the Fierce Digital Platform. | Fierce Digital Platform Overview
| All Fierce participants | Celebrate and Recognize | Within 2 weeks of first workshop | Internal Sponsor/ Executive Team | Email/TownHall/ Blog/Newsletter | Monthly/ Quarterly | Recognize employees for attending and applying Fierce concepts - include list of Fierce trained participants - provide testimonials from participants on how they've utilized the Fierce concepts - provide testimonials from supervisors of participants on how they've seen tangible outcomes - include reminders of future Fierce modules and Fireside chats | Recognition Email/Newsletter Template
| All Fierce participants | Fierce Fireside Chats | 30-45 days after first cohort completes workshop | Internal Sponsor | Group Meeting | Quarterly | Build a Fierce community within the organization by inviting past Fierce participants to an informal gathering where they can ask questions, share how they've applied Fierce concepts, connect with others, and get a refresher on Fierce concepts. | Fireside Chat Invitation Email Template
Fireside Chat Invitation Reminder Template
Fierce Fireside Chat Powerpoint Q1
Fierce Fireside Chat Powerpoint Q2
Fierce Fireside Chat Powerpoint Q3
Fierce Fireside Chat Powerpoint Q4
Learning Refreshers & Knowledge Check
Phase | Audience | What | When | Who | How | Frequency | The Message | Templates and Resources
IV: Evaluation/ROI | All Fierce participants | Fierce Feedback Survey | Once | Fierce Facilitator | Survey | After every workshop | Invite learners to share their intial reactions at the end of attending a Fierce workshop. | Fierce Feedback Survey
| All Fierce participants | Feedback Loop | Quarterly | Internal Sponsor | Survey | Quarterly | Fierce provides program measurement resources to support data collection on how your employees are translating the Fierce workshops into applicable behavior changes that impact business results. While Fierce hosts two key surveys (Feedback and Benchmarking Surveys), you are invited to create your own assessments using these resources. | Fierce Program Measurement Resources - Fierce Integration Success Suggestions - Kirkpatrick 4 levels of evaluation - Level 1: Post Workshop Feedback Survey - Level 2: Learning Refreshers & Knowledge Check - Level 3: Suggested Assessment Questions - Level 4: Fierce Benchmarking Survey - Level 4: Fierce Factor Organizational Assessment - Level 4: Fierce Factor Individual Assessment
| All Fierce participants | Post-Fierce Benchmarking Survey | Once | Internal Sponsor | Survey | 90 days after Fierce workshop | Invite learners who have completed the Fierce training series to take the post-workshop Benchmarking survey. - reach out to your Fierce Account Manager to get the formal report after your learners of completed it. | Fierce Benchmarking Survey
| Key Stakeholders | Fierce Impact Presentation | After 2nd Benchmarking Survey has been completed by learners | Internal Sponsor | Presentation | As needed | Measure how business outcomes have been impacted by Fierce programming | Fierce Impact Presentation Template

## Resource List
1. Introductory Communications
Company Wide Fierce Program Introduction Email Template
Company Wide Digital Platform Introduction Email Template
Introduction Email Template for Executive Leaders
Introduction Email Template for Managers
Introduction Email Template for Employees
Introduction Email Template for Pilot Participants
Post Pilot Workshop Email Template
Fierce Conversations Program Overview
Introduction to Fierce Presentation Template for Leaders
Introduction to Fierce Presentation Template for Employees
2. Workshop Reminders
General Pre-Workshop Email Template
Fierce Foundations Reminder Email
Fierce Team Reminder Email
Fierce Coach Reminder Email
Fierce Delegate Reminder Email
Fierce Accountability Reminder Email
Fierce Feedback Reminder Email
Fierce Confront Reminder Email
Fierce Negotiation Reminder Email
Fierce Foundations Post Workshop Email
Fierce Team Post Workshop Email
Fierce Coach Post Workshop Email
Fierce Delegate Post Workshop Email
Fierce Accountability Post Workshop Email
Fierce Feedback Post Workshop Email
Fierce Confront Post Workshop Email
Fierce Negotiations Post Workshop Email
3. Sustainability Programs
Recognition Email Template
Fireside Chat Invitation
Fireside Chat Q1 Reminder Templates
Fireside Chat Powerpoint for Q1
Fireside Chat Powerpoint for Q2
Fireside Chat Powerpoint for Q3
Fireside Chat Powerpoint for Q4
Manager Conversation Starters 1 Pager
Manager Conversation Starters Complete List
Sustainability Guide
4. Fierce Program Measurement
Fierce Integration Success Suggestions
Fierce Feedback Survey
Fierce Fireside Chat Prompts & Quizzes
Fierce Suggested Assessment Questions
Fierce Benchmarking Survey
Fierce Factor Organizational Assessment
Fierce Factor Individual Assessment
Fierce Impact Report Presentation Template